## Start Here
Zero → Expert: .NET Full Stack · Architect · AI/LLM
Personal interview-prep roadmap for Anil Kumar Sharma · ~10 months @ 12 hrs/week · built June 2026
THE GOAL
Rebuild your fundamentals so deeply that you can defend EVERY line of your CV live — in coding, pair-programming, and system-design rounds.
You have 10+ years of real delivery experience. This plan is not about learning from scratch — it's about converting 'I've seen it' into 'I can do it cold, while someone watches.'
THE 4 PROBLEMS WE'RE FIXING
1. Live coding / pair programming — you freeze when writing code in real time. Fix: daily reps + think-aloud drills (Phases 1-3 + Week 39).
2. System design rounds — Fix: dedicated architecture phase + 6 timed design mocks (Phase 4 + Weeks 37-38).
3. CV claims you can't back up (Azure especially) — Fix: an honest 'CV Defense' sheet + a real Azure phase where you actually build & deploy (Phase 5).
4. DSA / algorithms — Fix: one pattern per week, every week, all 40 weeks (NeetCode roadmap).
HOW TO USE THIS WORKBOOK
• Weekly Tracker — your week-by-week plan. Update the Status dropdown as you go. This is your home base.
• Resources & eBooks — every book, course, and free resource, organised by topic and priority.
• DSA Tracker — the 18 patterns; log problems solved per pattern.
• System Design — checklist of topics + practice prompts to attempt and self-score.
• CV Defense — go claim-by-claim through your resume: can you demo it live? Close every 'No'.
• Projects — 5 capstone builds. Each one produces real evidence for a CV claim (and great interview stories).
• Mock Interviews — log every mock, score it, and write the one thing to fix next time.
THE RULES (read these)
1. Code every single day, even 20 minutes. Reps beat marathons for fixing the 'freeze'.
2. Build, don't just watch. A video watched is forgotten; a feature shipped is remembered.
3. Think out loud whenever you code. Pair-programming is judged on your reasoning, not just the answer.
4. No new CV claim until you've built the thing. Earn the line, then write it.
5. Do timed mocks early and often — discomfort now is the whole point.
6. Adjust dates freely. 12 hrs/week is the assumption; the sequence matters more than the calendar.
AN HONEST NOTE ON THE CV
Your current resume lists Azure (App Service, Functions, Service Bus, AKS, AZ-400) and AI/LLM work as core strengths. You've said the Azure depth isn't real yet.
That's exactly what Phase 5 (Azure) and Phase 6 (AI/LLM) make true. By the time you finish those phases and Projects 4 & 5, every one of those lines becomes something you've actually done — deployed, debugged, and can whiteboard.
Until then: in interviews, speak to what you can defend. The CV Defense sheet tells you, line by line, where you stand today.

## Roadmap Overview
Roadmap Overview — 7 Phases
Layered path: Full Stack → Architecture → Azure → AI/LLM, with DSA & live-coding running the whole way through
Phase | Weeks | Theme | What you'll be able to do by the end | Capstone / Milestone
Phase 1 | 1–6 | C# & .NET Core Reset | Write idiomatic modern C# cold: OOP/SOLID, generics, LINQ, async/await, DI, unit testing. No more fumbling syntax in pair programming. | C# fundamentals self-assessment
Phase 2 | 7–12 | ASP.NET Core, APIs & EF Core | Build a secured, tested, production-shaped REST API from an empty folder — middleware, EF Core, JWT/OAuth2, versioning, caching. | Project 1: Secured Web API
Phase 3 | 13–18 | Frontend & Full-Stack | Build SPAs in both Angular and React, wire them to your API, containerise and deploy. TypeScript + JS internals solid. | Project 2: Full-stack app in Docker
Phase 4 | 19–24 | Architecture & Design | Apply SOLID, design patterns, Clean Architecture, DDD, CQRS and microservices — and explain the trade-offs out loud. | Project 3: Microservices demo
Phase 5 | 25–30 | Azure Deep-Dive (the real gap) | Actually deploy, secure, monitor and operate apps on Azure. Turn AZ-204/AZ-305 knowledge into hands-on muscle memory. | Project 4: App live on Azure (AZ-204 ready)
Phase 6 | 31–36 | AI / LLM Engineering | Build RAG pipelines, agents and LLM features with Azure OpenAI + Semantic Kernel — for real, matching your XEDI claims. | Project 5: LLM-powered feature
Phase 7 | 37–40 | Interview Mastery | Pass system-design, live-coding and CV-deep-dive rounds with composure. Behavioural STAR stories ready. | Interview-ready → start applying

## Weekly Tracker
Weekly Tracker — 40 Weeks
12 hrs/week ≈ 8 hrs core topic + 3 hrs DSA + 1 hr mock/review. Update the Status dropdown each week.
Wk | Target date | Phase | Primary focus | Key topics to master | Hands-on task (build something) | DSA pattern this week | Primary resource | Hrs | Status | Notes
1 |  | P1 | C# language core | Value vs reference types, stack/heap, boxing, structs, enums, string handling, var/const | Solve 20 Exercism C# exercises; rebuild a CLI calculator | Arrays & Hashing | C# 12 in a Nutshell | 12 | Not Started
2 |  | P1 | OOP & SOLID in C# | Classes/interfaces/abstract, inheritance vs composition, the 5 SOLID principles in C# | Build a Library console app applying all 5 SOLID principles | Two Pointers | Pro C# 10 (Troelsen) | 12 | Not Started
3 |  | P1 | Generics, collections & LINQ | List/Dictionary/HashSet, IEnumerable vs IQueryable, LINQ deep (deferred exec, joins, grouping) | Refactor week-2 app to LINQ; 15 LINQ katas | Sliding Window | C# in Depth (Skeet) | 12 | Not Started
4 |  | P1 | Async, await & concurrency | Task vs Thread, async/await internals, deadlocks, cancellation, IAsyncEnumerable | Build an async multi-file downloader with progress + cancellation | Stack | Concurrency in C# Cookbook (Cleary) | 12 | Not Started
5 |  | P1 | Modern C# features | Records, pattern matching, nullable refs, delegates/events, Func/Action, expression trees | Event-driven mini pub/sub app using events & delegates | Linked List | C# 12 in a Nutshell | 12 | Not Started
6 |  | P1 | Testing & DI foundations | xUnit, Moq, AAA, TDD, IDisposable, the DI container, lifetimes | TDD kata (Bank account) with xUnit + Moq; 90%+ coverage | Binary Search | DI Principles & Patterns (Seemann) | 12 | Not Started
7 |  | P2 | ASP.NET Core fundamentals | Hosting model, middleware pipeline, configuration, options pattern, DI in ASP.NET | Build a Minimal API + a controller API side by side | Trees (DFS) | ASP.NET Core in Action (Lock) | 12 | Not Started
8 |  | P2 | REST API design | Routing, model binding, validation, status codes, REST maturity, content negotiation | Build a full CRUD Web API for a 'Tasks' domain | Trees (BFS) | Pro ASP.NET Core (Freeman) | 12 | Not Started
9 |  | P2 | EF Core | DbContext, migrations, relationships, loading strategies, query perf, transactions | Add EF Core + SQL Server to the API; write migrations | Binary Search Trees | EF Core in Action (Jon Smith) | 12 | Not Started
10 |  | P2 | AuthN / AuthZ & security | JWT, OAuth2/OIDC, ASP.NET Identity, claims/policies, OWASP Top 10 | Add JWT auth + role/policy authorization to the API | Heap / Priority Queue | ASP.NET Core security docs | 12 | Not Started
11 |  | P2 | API hardening | Versioning, global error handling, Serilog logging, Swagger, pagination, Redis caching, rate limiting | Harden the API: versioning + Redis cache + Swagger + logging | Backtracking | Microsoft Learn (ASP.NET Core) | 12 | Not Started
12 |  | P2 | API testing | Integration tests, WebApplicationFactory, Testcontainers, mocking external deps | Write integration + unit test suite → ship PROJECT 1 | Graphs (intro) | Milestone: Project 1 | 12 | Not Started
13 |  | P3 | TypeScript & JS internals | Types, generics, closures, prototypes, event loop, promises, modules | TS exercises; convert a JS snippet library to typed TS | Graph DFS/BFS | TS Handbook + You Don't Know JS | 12 | Not Started
14 |  | P3 | Angular fundamentals | Components, services, DI, data binding, RxJS observables, HttpClient | Build an Angular CRUD UI against your Project 1 API | Topological Sort | Pro Angular (Freeman) + angular.dev | 12 | Not Started
15 |  | P3 | Angular advanced | Reactive forms, routing/guards, interceptors, state, lazy loading, change detection | Finish the Angular SPA: auth flow + forms + routing | Union-Find | angular.dev guides | 12 | Not Started
16 |  | P3 | React fundamentals | JSX, hooks (useState/useEffect), props, lifting state, controlled forms | Rebuild one Angular feature in React | 1-D Dynamic Programming | react.dev + The Road to React | 12 | Not Started
17 |  | P3 | React advanced | Context, custom hooks, React Query/data fetching, memoization, performance | Add data fetching + caching + perf tuning to the React app | 2-D Dynamic Programming | react.dev + TanStack Query docs | 12 | Not Started
18 |  | P3 | Full-stack integration | CORS, env config, Dockerfile, docker-compose, multi-container local run | Containerise SPA + API → ship PROJECT 2 | Greedy | Docker docs + Milestone: Project 2 | 12 | Not Started
19 |  | P4 | Patterns & SOLID (applied) | GoF essentials: Factory, Strategy, Observer, Decorator, Adapter, Repository, Unit of Work | Refactor Project 1 introducing 4+ patterns intentionally | Intervals | Head First Design Patterns / Refactoring.Guru | 12 | Not Started
20 |  | P4 | Clean Architecture | Layering, dependency rule, ports & adapters, use-cases, vertical slices | Restructure the app to Clean Architecture (Ardalis template) | Matrix / Grid | Clean Architecture (Martin) + Ardalis template | 12 | Not Started
21 |  | P4 | Domain-Driven Design | Entities, value objects, aggregates, bounded contexts, ubiquitous language | Model a non-trivial domain (e.g. ordering) with DDD tactical patterns | Tries | DDD Distilled (Vernon) | 12 | Not Started
22 |  | P4 | CQRS & event-driven | Commands/queries, MediatR, domain events, the outbox pattern, eventual consistency | Add CQRS + MediatR + domain events to the app | Bit Manipulation | Microsoft eShopOnWeb / Jimmy Bogard talks | 12 | Not Started
23 |  | P4 | Microservices | Decomposition, sync vs async comms, messaging (RabbitMQ / Service Bus / Kafka), API gateway | Split the monolith into 2 services + a message bus | Review weak patterns | Microservices Patterns (Richardson) | 12 | Not Started
24 |  | P4 | Resilience & observability | Polly (retry/circuit breaker/timeout), health checks, distributed tracing, OpenTelemetry | Add Polly + health checks + tracing → ship PROJECT 3 | Mixed timed set | .NET Microservices (free MS eBook) + Milestone | 12 | Not Started
25 |  | P5 | Azure foundations (for real) | Portal, resource groups, ARM/RBAC/IAM, networking basics, subscriptions, cost | Deploy a web app to Azure App Service from scratch | DSA maintenance set | MS Learn AZ-900 paths + John Savill (YouTube) | 12 | Not Started
26 |  | P5 | Azure compute | App Service deep, Azure Functions (triggers/bindings), Container Apps, AKS basics | Build + deploy an Azure Function (queue-triggered) | DSA maintenance set | MS Learn AZ-204 | 12 | Not Started
27 |  | P5 | Azure data & messaging | Azure SQL, Cosmos DB, Blob Storage, Service Bus, Azure Cache for Redis | Wire your app to Azure SQL + Service Bus queue | DSA maintenance set | MS Learn AZ-204 | 12 | Not Started
28 |  | P5 | Azure security & config | Key Vault, Managed Identity, App Configuration, Entra ID, RBAC scopes | Move all secrets to Key Vault + use Managed Identity | DSA maintenance set | MS Learn AZ-204 | 12 | Not Started
29 |  | P5 | Azure DevOps & monitoring | CI/CD (Azure Pipelines / GitHub Actions), App Insights, Log Analytics, Bicep IaC | Build a CI/CD pipeline that deploys to Azure + App Insights | DSA maintenance set | AZ-400 material (make your cert real) | 12 | Not Started
30 |  | P5 | Architecting on Azure | Well-Architected Framework, HA/DR, scaling, cost optimisation, reference architectures | Deploy full app end-to-end on Azure → PROJECT 4 (book AZ-204) | DSA maintenance set | AZ-305 path + Azure for Architects (Modi) | 12 | Not Started
31 |  | P6 | LLM foundations | Tokens, embeddings, context windows, temperature, prompting patterns, hallucination | Call Azure OpenAI from .NET; build a prompt library | DSA maintenance set | DeepLearning.AI short courses + Prompt Eng Guide | 12 | Not Started
32 |  | P6 | Semantic Kernel | SK kernels, plugins, functions, planners, chat completion, memory | Build an SK app with 2 custom plugins | DSA maintenance set | MS Learn GenAI + Semantic Kernel docs | 12 | Not Started
33 |  | P6 | RAG | Chunking, embeddings, vector stores (Azure AI Search / pgvector / Qdrant), retrieval | Build a RAG pipeline over a document set with citations | DSA maintenance set | DeepLearning.AI RAG course + Azure AI Search docs | 12 | Not Started
34 |  | P6 | AI agents | Function/tool calling, ReAct, planning, multi-step orchestration, guardrails | Build an agent that calls your Project-1 API as a tool | DSA maintenance set | SK Agents docs + AI Engineering (Huyen) | 12 | Not Started
35 |  | P6 | Evaluation & safety | LLM eval metrics, groundedness, prompt-injection defence, cost & latency control | Add evaluation harness + guardrails to the RAG app | DSA maintenance set | LLM Engineer's Handbook | 12 | Not Started
36 |  | P6 | Productionising LLM apps | Streaming, caching, prompt management, observability, responsible AI | Ship an LLM feature into Project 2 → PROJECT 5 | DSA maintenance set | Azure OpenAI docs + Milestone: Project 5 | 12 | Not Started
37 |  | P7 | System design intensive | Framework, capacity estimation, load balancing, caching, DB sharding, queues, CAP | Do 3 timed design problems (URL shortener, news feed, chat) | System-design focus | System Design Interview Vol 1 (Xu) + DDIA | 12 | Not Started
38 |  | P7 | System design advanced | Consistency, replication, search, rate limiting, notification systems, payment systems | Do 3 more designs; record yourself explaining each | System-design focus | System Design Interview Vol 2 (Xu) + ByteByteGo | 12 | Not Started
39 |  | P7 | Live coding & pair programming | Think-aloud, clarifying questions, tests-first, communicating trade-offs under pressure | 4 mock interviews (Pramp / interviewing.io); review tapes | Cracking-CCI sets | Cracking the Coding Interview (McDowell) + Pramp | 12 | Not Started
40 |  | P7 | CV defense & behavioural | Walk every CV line, STAR stories, salary/negotiation, final dry-runs | Complete CV Defense sheet; 2 full mock loops → APPLY | Mixed final set | CV Defense sheet (this workbook) | 12 | Not Started

## Resources & eBooks
Resources & eBooks — Curated
Don't buy everything. Start with the ★ Must-have in each category; the rest are reference/depth.
Category | Type | Title | Author / Source | Cost | Priority | Notes | Status
C# / .NET | Book | C# 12 in a Nutshell | Joseph & Ben Albahari | Paid | ★ Must | The single best C# reference; keep it open while you code
C# / .NET | Book | C# in Depth (4th ed) | Jon Skeet | Paid | High | Deep on LINQ, generics, async — read after the Nutshell
C# / .NET | Book | Pro C# 10 with .NET 6 | Andrew Troelsen | Paid | Med | Broad, beginner-friendly walkthrough of the language
C# / .NET | Book | Concurrency in C# Cookbook | Stephen Cleary | Paid | High | The reference for async/await & parallelism done right
C# / .NET | Book | DI Principles, Practices & Patterns | Mark Seemann | Paid | High | Makes DI and testable design click
C# / .NET | Site | Microsoft Learn — .NET | Microsoft | Free | ★ Must | Official, current, free. Primary source for everything .NET
C# / .NET | Practice | Exercism — C# track | Exercism | Free | ★ Must | Hands-on katas with mentor feedback — great for fixing 'freeze'
ASP.NET / API | Book | ASP.NET Core in Action (3rd ed) | Andrew Lock | Paid | ★ Must | The definitive ASP.NET Core book
ASP.NET / API | Book | Pro ASP.NET Core (10th ed) | Adam Freeman | Paid | High | Exhaustive, example-driven companion
ASP.NET / API | Book | Entity Framework Core in Action | Jon P Smith | Paid | ★ Must | Everything EF Core, with performance focus
Frontend | Book | Pro Angular | Adam Freeman | Paid | High | Pair with angular.dev for current APIs
Frontend | Site | angular.dev | Google | Free | ★ Must | Official, modern Angular docs & tutorials
Frontend | Book | The Road to React | Robin Wieruch | Paid | High | Best hands-on React intro (hooks-first)
Frontend | Site | react.dev | Meta | Free | ★ Must | Official React docs — the new ones are excellent
Frontend | Book | You Don't Know JS Yet (series) | Kyle Simpson | Free | High | Free on GitHub; fixes JS internals gaps
Frontend | Site | TypeScript Handbook | Microsoft | Free | ★ Must | Authoritative TS reference
Architecture | Book | Clean Architecture | Robert C. Martin | Paid | ★ Must | The vocabulary interviewers expect you to speak
Architecture | Book | Clean Code | Robert C. Martin | Paid | High | Classic; sharpens your pair-programming code quality
Architecture | Book | Head First Design Patterns | Freeman & Robson | Paid | High | Most approachable patterns book
Architecture | Site | Refactoring.Guru | Refactoring.Guru | Free | ★ Must | Patterns + refactorings, beautifully explained
Architecture | Book | Domain-Driven Design Distilled | Vaughn Vernon | Paid | ★ Must | Start here for DDD (short); then Implementing DDD
Architecture | Book | Implementing Domain-Driven Design | Vaughn Vernon | Paid | Med | The deep follow-up once DDD Distilled lands
Architecture | Book | Microservices Patterns | Chris Richardson | Paid | High | The microservices reference, .NET-friendly concepts
Architecture | eBook | '.NET Microservices: Architecture for Containerized Apps' | Microsoft (free PDF) | Free | ★ Must | Free, .NET-specific, ties to eShopOnContainers
Architecture | Repo | eShopOnWeb / eShopOnContainers | Microsoft / Ardalis | Free | High | Read real reference architectures' source code
System Design | Book | Designing Data-Intensive Applications | Martin Kleppmann | Paid | ★ Must | THE book on distributed data. Read slowly, all year
System Design | Book | System Design Interview Vol 1 | Alex Xu | Paid | ★ Must | Interview-shaped; do every problem
System Design | Book | System Design Interview Vol 2 | Alex Xu | Paid | High | More problems & depth
System Design | Book | Fundamentals of Software Architecture | Richards & Ford | Paid | High | For the architect-role lens & trade-off language
System Design | Site | ByteByteGo (newsletter/site) | Alex Xu | Free/Paid | Med | Visual primers; free archive is plenty to start
DSA | Book | Cracking the Coding Interview | Gayle L. McDowell | Paid | ★ Must | The interview-prep standard
DSA | Site | NeetCode (roadmap + 150) | NeetCode | Free/Paid | ★ Must | Follow the roadmap; one pattern per week in this plan
DSA | Book | Grokking Algorithms | Aditya Bhargava | Paid | Med | Gentle, visual intro if DSA feels rusty
DSA | Site | LeetCode | LeetCode | Free/Paid | High | Where you actually grind the problems
DSA | Practice | Pramp / interviewing.io | Pramp | Free | ★ Must | Free peer mock interviews — your live-coding cure
Azure | Course | MS Learn — AZ-204 path | Microsoft | Free | ★ Must | Developing Solutions for Azure — your core Azure cert
Azure | Course | MS Learn — AZ-305 path | Microsoft | Free | High | Designing Azure solutions — the architect cert
Azure | Video | John Savill's Technical Training | John Savill (YouTube) | Free | ★ Must | Best free Azure explainer on the internet
Azure | Book | Azure for Architects (3rd ed) | Ritesh Modi | Paid | Med | Architecture patterns on Azure
Azure | Book | Exam Ref AZ-204 | Microsoft Press | Paid | Med | Structured exam prep if you want a book
AI / LLM | Course | DeepLearning.AI short courses | Andrew Ng et al. | Free | ★ Must | RAG, function-calling, agents — short & practical
AI / LLM | Course | MS Learn — Develop GenAI with Azure OpenAI | Microsoft | Free | ★ Must | Azure-specific, matches your stack
AI / LLM | Docs | Semantic Kernel documentation | Microsoft | Free | ★ Must | .NET-first LLM orchestration — your CV's SK claim
AI / LLM | Book | AI Engineering | Chip Huyen | Paid | High | The systems view of building with LLMs
AI / LLM | Book | LLM Engineer's Handbook | Iusztin & Labonne | Paid | High | End-to-end LLM app engineering
AI / LLM | Site | Prompt Engineering Guide (promptingguide.ai) | DAIR.AI | Free | Med | Free, comprehensive prompting reference
Mindset | Book | A Philosophy of Software Design | John Ousterhout | Paid | High | Short; sharpens how you talk about design in interviews
Mindset | Book | The Pragmatic Programmer | Hunt & Thomas | Paid | Med | Career-long fundamentals & habits

## DSA Tracker
DSA Tracker — NeetCode Patterns
One pattern per week. Aim ~10-15 problems each. Confidence 4+ before you move on. Re-visit reds before interviews.
# | Pattern | Why it matters / typical questions | Target # problems | Solved | Confidence (1-5) | Status
1 | Arrays & Hashing | Frequency maps, dedup, prefix sums — appears everywhere | 15 | 0 |  | Not Started
2 | Two Pointers | Sorted-array pairs, palindromes, container problems | 12 | 0 |  | Not Started
3 | Sliding Window | Substrings, max/min window, longest/shortest-X | 12 | 0 |  | Not Started
4 | Stack | Valid parentheses, monotonic stack, expression eval | 12 | 0 |  | Not Started
5 | Binary Search | Sorted search, search-on-answer, rotated arrays | 12 | 0 |  | Not Started
6 | Linked List | Reversal, cycle detection, merge, fast/slow pointers | 12 | 0 |  | Not Started
7 | Trees (DFS/BFS) | Traversals, depth, path sums, level order | 18 | 0 |  | Not Started
8 | Binary Search Trees | Validate, insert/delete, kth element, LCA | 10 | 0 |  | Not Started
9 | Heap / Priority Queue | Top-K, merge-K, median stream, scheduling | 12 | 0 |  | Not Started
10 | Backtracking | Subsets, permutations, combinations, N-queens, word search | 14 | 0 |  | Not Started
11 | Graphs (DFS/BFS) | Islands, clone graph, connected components | 16 | 0 |  | Not Started
12 | Topological Sort | Course schedule, build order, dependency resolution | 8 | 0 |  | Not Started
13 | Union-Find | Connected components, redundant connection, accounts merge | 8 | 0 |  | Not Started
14 | 1-D Dynamic Programming | Climbing stairs, house robber, coin change, LIS | 16 | 0 |  | Not Started
15 | 2-D Dynamic Programming | Knapsack, edit distance, grids, longest common subseq | 14 | 0 |  | Not Started
16 | Greedy | Intervals, jump game, gas station, task scheduling | 12 | 0 |  | Not Started
17 | Intervals | Merge, insert, meeting rooms, min arrows | 8 | 0 |  | Not Started
18 | Bit Manipulation | XOR tricks, bit counts, subsets via bits | 8 | 0 |  | Not Started
|  | TOTAL | 219 | 0

## System Design
System Design — Topics & Practice
Top half: building-block concepts. Bottom half: practice problems to design end-to-end and self-score.
Area | Topic / concept to master | Self-score (1-5) | Status
Fundamentals | The interview framework: requirements → estimates → API → data model → high-level → deep dive → trade-offs |  | Not Started
Fundamentals | Back-of-envelope capacity estimation (QPS, storage, bandwidth) |  | Not Started
Fundamentals | Latency numbers every engineer should know; SLA/SLO/SLI |  | Not Started
Scaling | Vertical vs horizontal scaling; stateless services; load balancing (L4/L7) |  | Not Started
Caching | Cache strategies (write-through/back/aside), eviction, CDN, Redis |  | Not Started
Databases | SQL vs NoSQL, indexing, normalization, ACID vs BASE |  | Not Started
Databases | Replication, partitioning/sharding, consistent hashing |  | Not Started
Databases | CAP theorem, consistency models, eventual consistency |  | Not Started
Messaging | Queues vs streams, Kafka, pub/sub, back-pressure, exactly-once |  | Not Started
Patterns | CQRS, event sourcing, saga, outbox, idempotency |  | Not Started
Reliability | Rate limiting, circuit breakers, bulkheads, graceful degradation |  | Not Started
Reliability | Observability: logs, metrics, traces; health checks; alerting |  | Not Started
Security | AuthN/Z, token flows, secrets, encryption at rest/in transit |  | Not Started
Search/Other | Full-text search, geospatial, recommendation basics |  | Not Started
PRACTICE | Design a URL shortener (TinyURL) |  | Not Started
PRACTICE | Design a news feed / timeline (Twitter) |  | Not Started
PRACTICE | Design a chat system (WhatsApp) |  | Not Started
PRACTICE | Design a rate limiter |  | Not Started
PRACTICE | Design a notification system (ties to your GNE experience!) |  | Not Started
PRACTICE | Design a web crawler |  | Not Started
PRACTICE | Design an e-commerce checkout / payment system |  | Not Started
PRACTICE | Design a video streaming service (YouTube/Netflix) |  | Not Started
PRACTICE | Design a ride-hailing system (Uber) |  | Not Started
PRACTICE | Design a distributed cache |  | Not Started

## CV Defense
CV Defense — Line-by-Line Honesty Check
For every claim on your resume: be honest. 'No' is fine TODAY — the plan closes it. Never interview on a 'No' you haven't started.
CV claim / skill listed | Can you demo this LIVE today? | Evidence you can point to | Gap to close (action) | Covered in | Status
C# / ASP.NET Core / .NET 6-8 |  |  | Re-prove cold via Phases 1-2 + Project 1 | P1-P2 | Not Started
Angular SPA development |  |  | Build & deploy a real Angular SPA | P3 / Proj 2 | Not Started
React SPA development |  |  | Build the React version too | P3 / Proj 2 | Not Started
Entity Framework Core |  |  | Migrations + perf tuning in Project 1 | P2 | Not Started
REST API design & security (OAuth2/JWT, OWASP) |  |  | Implement auth end-to-end in Project 1 | P2 | Not Started
Microservices architecture |  |  | Actually split a system in Project 3 | P4 / Proj 3 | Not Started
Domain-Driven Design (DDD) |  |  | Model a domain with tactical DDD | P4 | Not Started
CQRS / Event-driven architecture |  |  | Add CQRS + MediatR + events | P4 | Not Started
Clean Architecture / SOLID |  |  | Restructure app to Clean Arch | P4 | Not Started
Azure App Service |  |  | Deploy for real (the big gap) | P5 / Proj 4 | Not Started
Azure Functions |  |  | Build a triggered function | P5 | Not Started
Azure Service Bus |  |  | Wire messaging in Project 4 | P5 | Not Started
Azure AKS / Kubernetes |  |  | Deploy a container to AKS basics | P5 | Not Started
Azure API Management |  |  | Front an API with APIM | P5 | Not Started
Application Insights / observability |  |  | Add telemetry in Project 4 | P5 | Not Started
Azure DevOps / CI-CD pipelines |  |  | Build a pipeline to Azure | P5 | Not Started
AZ-400 / AZ-204 / AZ-305 knowledge |  |  | Make the certs real via hands-on | P5 | Not Started
Docker / Kubernetes / Helm |  |  | Containerise in Project 2 & 3 | P3-P4 | Not Started
Kafka / RabbitMQ messaging |  |  | Use a real broker in Project 3 | P4 | Not Started
Redis caching / SQL perf tuning |  |  | Add caching + indexing in Project 1 | P2 | Not Started
Azure OpenAI / LLM integration |  |  | Build LLM feature in Project 5 | P6 / Proj 5 | Not Started
RAG (Retrieval-Augmented Generation) |  |  | Build a real RAG pipeline | P6 / Proj 5 | Not Started
Semantic Kernel |  |  | Build an SK app with plugins | P6 | Not Started
AI agents |  |  | Build an agent that calls tools | P6 | Not Started
Vector databases |  |  | Use Azure AI Search / pgvector | P6 | Not Started
xUnit / NUnit / TDD |  |  | Test-drive Project 1 | P1-P2 | Not Started
System design / scalable distributed systems |  |  | 6 timed designs in Phase 7 | P7 | Not Started

## Projects
Capstone Projects — Build Your Evidence
Five builds. Put each on GitHub with a clear README. These become your portfolio AND your interview stories.
# | Project | What you build | Skills / CV lines it proves | Done when… | Status
1 | Secured Web API | ASP.NET Core REST API: EF Core + SQL Server, JWT/OAuth2 auth, validation, versioning, Redis cache, Swagger, full test suite | C#, ASP.NET Core, EF Core, REST, security, Redis, xUnit | Deployed locally, >80% test coverage, public GitHub repo + README
2 | Full-Stack App (Angular + React + Docker) | Two SPAs (Angular and React) on top of Project 1's API, containerised with docker-compose | Angular, React, TypeScript, full-stack, Docker | Both SPAs run via one docker-compose up; auth flow works end-to-end
3 | Microservices Platform | Split into 2-3 services with a message broker (RabbitMQ/Service Bus), API gateway, Polly resilience, tracing | Microservices, DDD, CQRS, messaging, resilience, observability | Services communicate async; trace a request across services
4 | Cloud-Native on Azure | Deploy the platform to Azure: App Service/Functions, Azure SQL, Service Bus, Key Vault, App Insights, CI/CD pipeline | Azure (all of it), DevOps, IaC — closes your biggest CV gap | Live URL on Azure; pipeline deploys on push; telemetry visible
5 | LLM-Powered Feature | RAG pipeline + an AI agent over your own data using Azure OpenAI + Semantic Kernel, with eval & guardrails | Azure OpenAI, RAG, Semantic Kernel, agents, vector DB | Answers questions over your docs with citations; agent calls a tool

## Mock Interviews
Mock Interview Log
Do these from Week 12 onward — early and often. The discomfort is the training. Fill a row after every mock.
Date | Type | Platform / with whom | Topic / question | Score (1-5) | What went wrong | The ONE thing to fix next